**\*PROJECT TIMELINE TEMPLATE\***

**2-year Project Timeline: Healthy Native North Carolinians**

**Tribe or Organization:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Instructions: Please provide a timeline of your project activities for the 2-year grant period. Each activity listed in your proposal should be listed in the timeline. Dates can be specific, listed by month, or listed by season (spring, summer, fall, winter), where most applicable.

|  |  |  |
| --- | --- | --- |
| **When** | **What (Activity)** | **Who is assigned task?** |
| June-August 2016 | 5K Run planning meetings | Tribal Council 5K Subcommittee |
| June-August 2016 | 5K volunteer recruitment | Tribal Council 5K Subcommittee  |
| September 2016 | 5K Run | Tribal Council 5K Subcommittee and community volunteers |
|  |  |  |
|  |  |  |
| March-April 2017 | Purchase all equipment, tools, supplies, and seeds for making raised bed gardens | Tribal staff |
| April 2017 | Build raised beds | Tribal staff and youth  |
| May 2017 | Planting vegetables | Youth |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |